## Resp&Aud
ORDER | STAGES | DOCUMENTS | RESPONSIBILITY | [6 empty] | TYPE | AUDIENCE (Should SEE)
|  |  | CEO | GM | SM | PM | PL | TEAM | CL |  | CEO | GM | SM | PM | PL | TEAM | CL
1 | Proposal Preparation | Risk Management |  |  |  | 1 |  |  |  | doc | 1 | 1 | 1 | 1 | 1
2 |  | Proposal |  | 1 | 1 |  |  |  |  | doc |  | 1 | 1 | 1 |  |  | 1
3 |  | Contract |  | 1 | 1 |  |  |  |  | doc | 1 | 1 | 1 | 1 |  |  | 1
4 | Project Start-up | Project Startup | 1 | 1 | [5 empty] | doc | 1 | 1 | 1 | 1
5 |  | Resource Request Form |  |  |  | 1 |  |  |  | doc |  | 1 | 1 | 1 | 1
6 |  | Task Allocation Form |  |  |  |  | 1 |  |  | doc |  |  |  | 1 | 1 | 1
7 | User Requirement | Software Requirement Specification |  |  |  | 1 | 1 |  |  | doc |  |  | 1 | 1 | 1 | 1 | 1
8 |  | Change Request |  |  |  |  | 1 |  |  | doc |  |  | 1 | 1 | 1 | 1 | 1
9 | Project Planning | Software Development Plan |  |  |  | 1 | 1 |  |  | doc |  |  |  | 1 | 1
10 |  | Project Plan |  |  |  | 1 |  |  |  | mpp |  |  | 1 | 1 | 1 |  | 1
11 |  | Project Plan (Cover Page) |  |  |  | 1 |  |  |  | doc |  |  | 1 | 1 | 1
12 |  | Quality Plan |  |  |  | 1 |  |  |  | doc |  |  |  | 1 | 1
13 |  | Configuration Management Plan |  |  |  | 1 | 1 |  |  | doc |  |  |  | 1 | 1
14 |  | BackUp Plan |  |  |  | 1 |  |  |  | doc |  |  |  | 1 | 1
15 |  | BackUp Plan (Log) |  |  |  | 1 |  |  |  | doc |  |  |  | 1 | 1
16 | Study & Design | Detail Design Document |  |  |  |  | 1 |  |  | doc |  |  |  | 1 | 1 | 1
17 |  | Detail Design Document Excel File |  |  |  |  | 1 |  |  | xls |  |  |  | 1 | 1 | 1
18 |  | Report Design Document |  |  |  |  | 1 |  |  | doc |  |  |  | 1 | 1 | 1
19 |  | Technical Architecture Document |  |  |  |  | 1 | 1 |  | doc |  |  |  | 1 | 1 | 1
20 | Software Testing & Planning | Test Plan & Report |  |  |  |  | 1 |  |  | doc |  |  |  | 1 | 1 | 1 | 1
21 | Delivery & Installation | Implementation Plan |  |  |  |  | 1 |  |  | doc |  |  |  | 1 | 1 |  | 1
22 |  | Installation Manual |  |  |  |  | 1 |  |  | doc |  |  |  | 1 | 1 |  | 1
23 |  | User Manual |  |  |  | 1 | 1 |  |  | doc |  |  |  | 1 | 1 |  | 1
24 |  | Technical Manual |  |  |  | 1 | 1 | 1 |  | doc |  |  |  | 1 | 1 | 1 | 1
25 |  | User Acceptance Certificate |  |  | 1 | 1 | 1 |  | 1 | doc | 1 | 1 | 1 | 1 |  |  | 1
26 | Project Closure | Customer Feedback Form |  |  |  | 1 |  |  | 1 | doc | 1 | 1 | 1 | 1 |  |  | 1
27 |  | Project Closure Report |  |  |  | 1 |  |  |  | doc | 1 | 1 | 1 | 1 |  |  | 1
101 | Recurring Activities | Minutes of Meeting |  | 1 | 1 | 1 | 1 | 1 |  | doc |  | 1 | 1 | 1 | 1 | 1 | 1
102 |  | Weekly Status Report (External) |  |  |  |  | 1 |  |  | doc |  |  | 1 | 1 | 1 |  | 1
103 |  | Weekly Status Report (Internal) |  |  |  |  | 1 |  |  | doc |  |  | 1 | 1 | 1
104 |  | Project Status Report |  |  |  | 1 |  |  |  | doc | 1 | 1 | 1 | 1
105 |  | Review Records |  |  |  | Rewiewer |  |  |  | doc |  |  |  | 1 | 1
106 |  | Release Note |  |  |  | 1 |  |  |  | doc |  |  |  | 1 | 1
107 |  | Delivery Challan |  |  |  | 1 |  |  |  | doc |  |  |  | 1 |  |  | 1
108 |  | Delivery Records |  |  |  | 1 | 1 |  |  | doc |  |  |  | 1 | 1
201 | Others | Coding Standards |  |  |  | 1 | 1 |  |  | doc |  |  |  | 1 | 1 | 1
301 | Q C | Audit Review Comments |  |  |  | Q.A. Team |  |  |  | doc |  |  |  | 1 | 1
|  |  | 1 | 4 | 4 | 21 | 20 | 3 | 2 |  | 7 | 10 | 16 | 37 | 29 | 11 | 16